## Programme delivery
Targeted Intervention -Annual Evaluation Tool (FSW/MSM /TG/IDU TIs) - 2019-20
Name of the NGO:SOSVA |  |  |  |  | District:Chandigarh |  | State:Chandigarh
Program Delivery
Sl.No. | Indicators | Typology Applicable | Target | Achievement | Key Questions | Methodology to be adopted | Assessment Scores |  |  | Score Resulted | Explanation for score
S. no | [6 empty] | 1(Poor) | 2(Average) | 3(Good)
[7 empty] | 1 | 2 | 3
SECTION 1: BASIC SERVICES
OUT REACH
1 | Service delivery data of HRG maintained at outreach level. | FSW/MSM /TG/IDU | 100 % of active population | 910 | Whether PEs are maintaining the weekly planning and activity sheet (Format B/B_1) as per NACO's guideline. | Verify the master register of HRGs / line listing /weekly format B/B_1 of the last one quarter. Meeting with PEs should be conducted. | Form-B/B_1 is maintained by PEs but no prioritisation of HRG done by ORWs based on risk and vulnerability data. | Form-B/B_1 is maintained by PEs and proper prioritisation of HRG done by ORWs based on risk and vulnerability data. | Form-B/B_1 is maintained by PEs and proper prioritisation of HRG done by ORWs based on risk and vulnerability data. IPC and BCC sessions with HRG are conducted by PEs based on risk and vlunerability data as per format B/B_1. | 1 | Form-B/B_1 is maintained by PEs but no prioritisation of HRG done by ORWs based on risk and vulnerability data.
2 | Individual HRGs tracked for project services. | FSW/MSM /TG/IDU | Individual HRG tracking sheet |  | Individual HRG tracked for ICTC, RMC and Syphilis testing . Updation of Risk, vulnerability and condom demand needle/syringe data on quarterly basis. | Interview with M&E officer, Counselors and project manager. Soft or hard copy of individual HRG tracking sheet and quarterly updation of risk and vlunerability data | Individual HRG tracking sheet is available but not updated. Tracking sheet is also not used for planning and prioritization of HRGs. | Individual HRG tracking sheet is available and updated. Tracking sheet is not used for planning and prioritization of HRGs. | Individual HRG tracking sheet is available and updated. Data is used for planning and prioritization of HRG. Project and M&E officer are able to provide data on - how many HRG tested for HIV once and twice, how many hrg visited STI clinic once, twice, thrice erc. | 1 | Individual HRG tracking sheet is available but not updated. Tracking sheet is also not used for planning and prioritization of HRGs.
3 | Registration of HRG against target | FSW/MSM /TG/IDU | 100% of the Contract target | 800/883 | All HRG should be registered by ORW. Format-A should be properly filled and master registration sheet completed and to be computerised | Verify the computerised master register of HRGs , line listing and filled format-A (data filled for all indictors) for all the registered HRGs. Check for Drop-out records and TI to provide explanation in case of less than 100 % registration. | 70-80 percent of the target HRGs registered. | 81-90 percent HRGs were registered against the target | Above 90 percent HRGs were registered. | 3 | SACS assigned TI the target of 800. TI registered 883 IDUs in comparison to the target.
4 | Monthly activity calander and out reach plan for the TI staff is developed and adhered. | FSW/MSM /TG/IDU | Monthly review, Calander of activities & outreach plan for the current year. |  | Whether the monthly review is conducted, activity calander and out reach plan for the TI staff is developed, and revised plan for the subsequent month is developed. | Verify the monthly review minutes, calander, outreach plans, and relevant reports | Monthly meetings are conducted but not regular, calander of activities and outreach plan is not developed | Monthly meetings are regularly conducted and calander of activities and outreach plan is developed | Monthly meetings are regularly conducted, calander of activities and outreach plan is developed, performance is reviewed and follow up actions prompted. | 2 | A monthly meeting was held, but no out reach plan was developed, and no follow-up action was taken for out reach activities.
5 | Percent of target HRG reached by the project (As per contract) during last one year | FSW/MSM /TG/IDU | 100% of the active population/contract target | 746 | Average no. of HRGs were contacted at least once in every month with any or all project services by PEs during last one year | Verification of project proposal, ORW's format-C and monthly CMIS report. At least 20% of the randomly selected HRGs of selected hotspots need to be verified during the hotspot visits.80% of the population and Line list ID numbers is to be constant. Cross verify with indicator for micro plan. Verify the remaining HRG taking services regularly by the TI. | 60-70% of target population were provided with any/all project services i.e. condom, needle/syringe, STI, ICTC and BCC/IPC services every month during the contract period | 71-80% of target populationn were provided with any/all project services i.e. condom, needle/syringe, STI, ICTC and BCC/IPC services every month during the contract period | Above 80% of target population were provided with any/all project services i.e. condom, needle/syringe, STI, ICTC and BCC/IPC services every month during the contract period | 3 | All project services were provided to 94% of the target population (746/800)
6 | Regular Contact - NSP (No. of individuals target HRG contacted with any or all project services - NSEP/BCC/IEC/Referral | IDU | 100% of contract target every month | 800 | Average no. of IDUs that were contacted at least 2 days in a week for the purpose of NSEP/BCC/IEC/Referral | PE form-B and ORW's format C and PE diaries . At least 20% of the randomly selected IDU need to be verified during above during hotspot visits. | 60-70% of target group are contacted at least 2 days in a week for the purpose of NSEP/BCC/IEC/Referral | 71-80% of target group are contacted at least 2 days in a week for the purpose of NSEP/BCC/IEC/Referral | Above 80% of target group are contacted at least 2 days in a week for the purpose of NSEP/BCC/IEC/Referral | 3 | According to the peer diary, 94% of HRGs are regularly reached out to with one-on-one and one-on-one group services, as well as N/S and condom services, on a monthly basis. However, during discussions with HRGs, this was not reflected in the field.
7 | Field visit by ORWs | FSW/MSM /TG/IDU |  |  | ORW visiting the field minimum 5 days in a week and providing supportive supervision to all the PEs of his/her areas for effective delivery of project services by PEs to HRGs and to ensure all the PEs have required skills. | ORW diaries, weekly staff meeting minutes, ORW movement plan/register and Form D. The same should be verified with the community and stakeholders during the hotspot visits | All PE have been met at the hotspot and provided support by ORW at least twice in a month | All PE have been met at the hotspot and provided support by ORW four times in a month | All PE have been met at the hotspot and provided support by ORW more than four times in a month and all hotspots are covered in a month | 3 | ORW has met with all PE at the hotspot and provided support more than four times in a month, and all hotspots are covered in a month.
8 | Individual New HRGs registred during the year for any project services. | FSW/MSM /TG/IDU | 20 % of MOU target with in a Year | 66 | Whether Outreach team registred new HRGs. | Verify the master register of HRGs / Registration form "A" | New HRG registred up to 10% against the Annual Target | New HRG registred up to 15 % against the Annual Target | New HRG registred up to 20% against the Annual Target | 1 | 8.25 % new HRG regsitred against the Annual Target of 800.
9 | Strengthining outreach activities aginst the plan by the TIs. | FSW/MSM /TG/IDU | 24 health camp | 18 | How many Health Camp were planned to reach out the hard to reach population | Discussion with the staff and verifying the registers | Less 50% | 51%-79% | 80 % and above | 3 | There were 24 Health Camps planned, with 18 taking place during the evaluation period.(075%)
10 | Number of HRG identified, registred, and reached from verious networks (Social Network, Virtual Networks, etc) | FSW/MSM /TG/IDU |  | 0 | Whether Outreach team was able to identify the HRGs operating through various social networks and virtual network and how many of them are registred and reached | Discussion with the staff/ Line list/ Services | Identified various social/virtual networks, listed the networks and line list of HRGs available with the project | Registered at least 60% of the line listed HRGs | Reached at least 80% of the registered HRGs with services. | 0 | There has been no new registration through the social networking site.
11 | Established STI clinic / PPP /Government STI clinics linkages | FSW/MSM /TG/IDU | STI Services should be established | 2 | Set-up of STI clinic / PPP/ linkages developed with DSRC/Govt. Hospital as per NACO guideline. | Observations should be made based on NACO guidelines. Project STI Clinic, PPP registers and payment registers to be verified. | Project STI clinic / PPP linkages has been set-up but not as per NACO guideline. | STI clinic / PPP linkages in place but registers / patient card (Network clinic format) are not maintained as per NACO guideline at clinic | STI clinic / PPP linkages in place and requisite registers / patient card (Network clinic format) are maintained at clinic. | 3 | There is a STI clinic in place, and the necessary registers / patient cards (Network clinic format) are kept at the clinic. The STI Clinic is serviced by one MBSS doctor.
12 | HRG attending STI clinics (Project based/ PPP /Government STI clinic) are counselled | FSW/MSM /TG/IDU | 100% of clinic attendees | 0 | No. of HRG visiting to clinics are counselled. | Counselling registers, STI register and monthly CMIS/SIMS report. Interaction with STI providers/counsellors/ANM | 60-70% of HRGs attending STI clinic were counselled. | 71- 80% of HRG attending STI clinic were counselled. | Above 80% of HRG attending STI clinic were counselled. | 0 | The TI has not counselled HRG, who attends the STI clinic.
13 | HRGs attending clinic for STI services such as RMC/GMC, Symptomatic and Presumptive in last one year | FSW/MSM /TG | 4 times in a year of contract target | 746 | No.of HRGs attending regular medical check-up/general medical check-up (for IDU) four times during last one year | PEs Form-B/B_1, STI registers / tracking sheet, ORW form-c field diary, referral slips/registers, Payment register/slips of PPP doctors and monthly CMIS report | 60-70% of the individual HRGs had undergone for RMC twice in past one year. | 71- 80% of the individual HRGs had undergone for RMC twice in past one year. | Above 80% of the individual HRGs had undergone for RMC twice in past one year. | 3 | Over 93% of individual HRGs have been performed for GMC twice a year.
14 | Newly registered asymptomatic HRGs provided presumptive treatment (PT) during last one year | FSW/MSM /TG | 100% of newly registered HRGs |  | No. of new HRG registered during last one year and received PT | STI CMIS/SIMS reports, Referral register, referral slips | 50-60% newly registered HRG provided PT. | 61- 70% newly registered HRG provided PT . | Above 70% newly registered HRG provided PT. | 2 | 61- 70% newly registered HRG provided PT .
15 | Percent of HRGs tested for Syphilis | FSW/MSM /TG/IDU | 2 times in a year of contract target | 957 | Percent of individual HRGs tested for Syphilis during last one year | STI CMIS/SIMS reports, Referral register, referral slips, individual tracking sheet | 30-40% of HRGs underwent Syphilis test | 41-50% of HRGs underwent Syphilis test | Above 50% of the HRGs underwent Syphilis test | 3 | Above 50 % of thre HRG underwent syphillis
16 | Percent of individual HRGs tested for HIV during last one year | FSW/MSM /TG/IDU | 100% line listed HRG | 93 | No. of line listed individual HRGs tested for HIV during last one year | Referral registers, referral slips and PE form-B/B_1 and ICTC data. Verify the referral slips signed by the ICTC counsellors and POD no. provided. | 40-50% of the HRGs underwent HIV test twice during contract period | 51-60% of the HRGs underwent HIV test twice during contract period | Above 60% of the HRGs underwent HIV test twice during contract period | 0 | Only 11.3 % of the HRG underwent HIV test twice during the contact period
17 | Percentage of HRG tested positives are registred at ART centre | FSW/MSM /TG/IDU | 100% of HRG tested positive | 18 | No. of positive HRGs registered at ART centre during last one year | Verify with the ART centre, referral register | 50-60% of the total identified positive HRGs linked to ART | 61-70% the total identified HRGs linked to ART | Above 70% HRGs linked to ART | 3 | All the HRG positive patients has been linked to the ART centree
18 | Abscess Management | IDU | HRGs reported with abscess |  | Proper dressing and treatment for all abscess cases under aseptic conditions at the clinic and through outreach | Clinic records, inspection of DIC, and interaction with clients | Aseptic abscess management services established for limited time | Aseptic abscess management services established and available to for entire day | Aseptic abscess management services established and available to entire day and abscess management also taken by ANM in the field | 3 | Aseptic abscess management services established and available to entire day and abscess management also taken by ANM in the field
| No of Active Spoused and Partner identified in project. | IDU | Number of active spouses identified during the project. | 376 | How many IDUs are married and having regular partner as per the master register | Verifiy the Master register/ Female ORW DIARY/ referral slips/ | Please specify the number to be linked with indicator 19, which will be the denominator for indicator 19 |  |  | 3 | 376 are married and having regular partner as per the master register
19 | Number of active spouses and partners tested from the identified IDUs by the project. | IDU | Please collect the information from the project | 238 | Partners and spouses are tested against the identified by the project. | Verifiy the Master register/ Female ORW DIARY/ referral slips/ | Less 50% tested | 50% to 79% tested | more than 79% tested | 2 | 63.2 % of the tested against the idetified by the project
20 | Number of active spouses and partners identifed and positives linked to ARTC. | IDU | Total positive Identified | 2 | Partner and spoused are registred at ARTC. | Verifiy the Master register/ Female ORW DIARY/ referral slips/ | Less 50% tested | 50% to 79% tested | more than 79% tested | 3 | All are linked to ART centre.
21 | 20% of the existing active IDU population has been put on OST | IDU | 20 % of the Active Population. | 355 | How many IDUs are currently on OST | Registration/ Reports/Service Directry | 10-15 % of HRGs registed at OST and are active | 16 -20 % of HRGs registed at OST and are active | Above 20 % of the HRGs registed at OST and are active | 3 | Arounf 45 % of the HRG regsistere at the OST
COMMODITIES
22 | Individual HRGs are getting Needle and Syringes as per N/S demand analysis | IDU | 100 % of distribution against N/S demand | 150038 | N/S distribution should be made as per demand/ requirement gap analysis. | Verification of individual peer form "B_1" and ORW form "C". Verification to be done during hotspot visit | N/S gap analysis done and at 50-55% of individual HRGs distributed against the requirement. | N/S gap analysis done and at 56-65% of individual HRGs distributed against the requirement. | N/S gap analysis done and at least Above 65% of individual HRGs distributed against the requirement. | 3 | 71684 syringes were distributed in response to a demand of 74938 (95.6%). Similarly, 150038 needles were requested and 142428 were distributed.(94.9%)
23 | NSEP: Needle/Syringe Return Rate | IDU | 80% of distributed needles/syringes should be returned / collected after use |  | Percentage of needles/syringes distributed to IDUs being returned / collected after use for safe disposal | Verification of PE & ORW diary, DIC record, disposal register | 30-40% of used needles/syringes being returned/collected for safe disposal | 41-50% of used needles/syringes being returned/collected for safe disposal | More than 50% of used needles/syringes being returned/collected for safe disposal | 2 | More than 50 % of the used needles/syringes being returned/collected for safe disposal
24 | Bio-medical Waste (BMW) Management | FSW/MSM /TG/IDU | 100 % of bio-medical waste from CBS being disposed off safely |  | Whether BMW guidelines are being followed for the safe disposal of waste generated in the TI programme. | Verification of PE & ORW diary, DIC record, disposal register, photographs | Waste Disposal mechanism in place but only collection of waste is being done as per the guidelines | Waste Disposal mechanism in place but only collection and disinfection is being done as per guidelines | Waste Disposal mechanism in place: collection, disinfection and final disposal being done as per guidelines | 3 | Waste Disposal mechanism in place: collection, disinfection and final disposal being done as per guidelines
18 | Availability of drugs for STI treatment and Abscess management, with a buffer stock management in place. | FSW/MSM /IDU | 3 months buffer stock based on average monthly consumption |  | No. of times STI drugs, have been purchased/supply during the contract period. Was there any stock-out of commodities reported during contract period. If the supply is an issue from SACS, the indicator to be verified for the period when stock was available. | Verification of stock & distribution register and vouchers. Ask question about buffer stock system to project manager/ANM/Counsellor. | Reported stock-out of STI drugs during contract period | No stock out reported during contract period but buffer stock system was not followed as per guideline | No stock out reported during contract period and buffer stock system was maintained as per guideline.
SECTION 2: SUPPORT SERVICES
25 | Identified cases from HRG were linked for TB to DOT centre (RNTCP) during the contract period | FSW/MSM /TG/IDU | 100% of all identified cases of TB |  | No. of target group member linked to DOT centre during the contract period, detected for TB. | Verification of registers, general treatment register, referral slips/register | 40-50% of the total identified HRGs linked to DOT | 51-60% of the total identified HRGs linked to DOT | Above 60% HRGs linked to DOT | 3 | All the TB positive linked to DOT centre.
ENABLING ENVIRONMENT
26 | Advocacy meeting with key stakeholders (health service providers, Police personnel, ICTC/ART centres, PRI, Social Welfare Dept., Gate Keepers, etc.) | FSW/MSM /TG/IDU |  |  | Advocacy meeting held with key stakeholders at various level with plan. | Verification of minutes, meeting registers and MIS reports | Advocacy meeting are conducted on need based with or with out | Advocacy meeting conducted at all levels as per plan without proper documentation and follow up | Advocacy meeting regularly conducted as per plan at all levels with proper documentation and follow-up | 3 | Advocacy meeting regularly conducted as per plan at all levels with proper documentation and follow-up
27 | Crisis management team in place | FSW/MSM /TG/IDU | To be addressed 100 % cases | 5 | Set up of crisis management team at TI level, No. of cases reported and solved within 24 hours | Advocacy activities/ Crisis management or meeting register/no. of harassment cases reported (If no such cases reported then verify during interaction with HRG whether they have faced any such harassment/violence/ crisis during the contract period). To review supporting financial documents. | Crisis management team addressed 60% of the cases all reported during last one year | Crisis management team addressed 61-70% of the cases reported during last one year. | Crisis management team addressed above 70% of the cases reported during last one year | 3 | Crisis management team addressed above 70% of the cases reported during last one year
COMMUNITY MOBILISATION
28 | Collectivisation (No. of HRGs part of committees /CBOs / support groups) | FSW/MSM /TG/IDU |  |  | No. of HRGs are part of committees /CBOs / support groups out of the total registered HRG with the project | Verification of records/minutes of Committees /CBO / support groups meetings against the HRG registration document (If CBO do not exist with TI then HRG representation in the committee should be considered) | At least 30 % of the (registered HRGs) are part of Committees /CBO/ / support groups | 30- 50% of the registered HRGs are part of Committees /CBO/ support groups. This should also include at least 30% are new HRGs registered more than 3 months | More than 50% of the registered HRGs are part of Committees /CBO / support groups. This should also include at least 50% are new HRGs registered more than 3 months | 0 | Few HRGs are part of DMC, PMC and Crisis management committee. However, no CBO/support group is formed, except SHG of spouses of HRG.
COMMUNITY RESPONSE TO THE PROGRAM SERVICES
29 | Project is adhering to confidentiality norms. | FSW/MSM /TG/IDU |  |  | Privacy in the clinic and information shared in the counselling sessions are maintained and not shared. | FGD with the 10-15 community members (suggested to conduct at the field). | 50%-60% participants are sure of confidentiality norms being adhered at the project level | Between 61% to 80% of the participants are satisfied with privacy and confidentiality at the project level. | Between 81% to 100% of the participants are satisfied with privacy and confidentiality at the project level. | 3 | Participants are satisfied with privacy and confidentiality at the project level.
30 | Community perception on project services | FSW/MSM /TG/IDU |  |  | Are the community members satisfied with the available services and services meet their demands. | FGD with 10-15 community members (suggested to conduct at the filed level). | 50%-60% participants are convinced with the project services | Between 61% to 80% of the participants are satisfied with the project services. | Between 81% to 100% of the participants are satisfied with the project services. | 3 | In the FGD conducted in field with HRGs, it is learned that HRGs are satisfied with the project activities.
31 | Adequate supply of commodities(Condoms/Lubricants /Needle and Syringes, drugs) | FSW/MSM /TG/IDU |  |  | Condoms, needle & syringe for IDUs and Lubricants for MSM provided by Project | FGD with 10-15 community members (Suggested to conduct at the filed. If the project is composite conduct the FGD separately). | 50%-60% participants are sure of confidentiality norms being adhered at the project level | Between 61% to 80% of the participants reported that they are getting the commodities as and when they demand. | Between 81% to 100% of the participants reported that they are getting the commodities as and when they demand. | 3 | During the FGD with the HRG it is observed that the HRG are getting all the required services as and when they demand. 24567 condoms were distributed against the demand of 27985
32 | Involvement of key stakeholders in programme monitoring | FSW/MSM /TG/IDU |  |  | Ability of the project to involve stakeholders like police, civic health service providers, social development sector officials in addressing the issues relating to project services | One to one interaction with at least 3 stakeholders of the project. (suggested to conduct at the filed). | One stake holders participated in addressing the issues relating to project services | Two stake holders have said S/he has involved in addressing the issues relating to project services. | All the three stake holders have said that they involved in addressing the issues relating to project services. | 3 | In one to one interaction with 4stakeholders, it is learnt, that all 4 are involved in addressing the issues relating to project services.
33 | Involvement of Counsellor / ANM | FSW/MSM /TG/IDU |  |  | The counsellor/Nurse should be sensitive while addressing issues relating to community members. | FGD with the 10-15 community members (suggested to conduct at the field level). | 50%-60% respondents reported that they are satisfied with the counsellor/ANM | Between 61% to 80% respondents reported that they are satisfied with the counsellor/ANM | Between 81% to 100% of the respondents reported that they are satisfied with the counsellor/ANM | 3 | HRG reported that they are satisfied with the counsellor/ANM.
34 | How many meetings conducted for community score card system in the year. | FSW/MSM /TG/IDU |  |  |  | Verify the filled in score coard, meeting minutes, and follow up actions. | 1 meeting conducted in a Year | 2 meetings conducted in a Year | 3 and more community meeting conducted in a Year | 3 | Four community meetings were held in order to create a community score card.
| SECTION 1: BASIC SERVICES | [6 empty] | SECTION 1: TOTAL MARKS OBTAINED |  | 56
| SECTION 2: SUPPORT SERVICES | [6 empty] | SECTION 2: TOTAL MARKS OBTAINED |  | 27
| * with regard to the commodities, the stock out experienced by TI may be taken in to consideration while scoring. | [8 empty] | 83

## Org capacity
TI -Annual Evaluation Tool (FSW/MSM/IDU)-2019
Name of the NGO:SOSVA |  |  | District:Chandigarh |  | State:
Organisational Capacity
Sl.No. | Indicators | Mean of verification/observations | Areas of assessment | Score Resulted | Explanation for score | Remarks
1 | At least All project staff and PE positions have been filled as per project proposal | All NGOs contracted has to appoint the staff within three months from signing of contract. Project proposal, appointment letters / staff attendance sheet during the last year (If a position has been vacated and not filled in within 2 months, give "0" mark for this indicator.) | Recruitment system | 1 | All project staff including Project Manager, M&E Officer and 7 ORWs (5 males and 2 females) were appointed. 18 out of 20 sanctioned Peer educators have been appointed till date.
2 | Staff turnover witnessed in the project during the contract period. | Attendance sheets /appointment letters. (If there is more than 60% of project staff except peer educators have resigned during the year then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | Institutional process | 1 | The project has seen very little staff turnover.
3 | PE turnover witnessed in the project during the contract period | Attendance sheets /appointment letters. (If there is more than 40% PEs turnover during the contract period then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | Administrative system | 1 | There has been no turnover among peer educators.
4 | 10% of the ORWs are from the community i.e. either the peer educators have been graduated to become ORWs or the community members are selected as ORWs | This process of selection of community members as ORWs should be atleast one year old. | Staffing | 1 | There are total 7 ORWs (5 males and 2 females). One out of the 5 male ORWs is from the community. This ORW is working in the project since the inception of the project.
5 | Ratio of PEs to HRG ( a ratio of 1: 60 for FSW/MSM & 1:40 for HTG & IDUs) | Line listing of HRGs and number of PEs/VPL on board. (A 20% Variation may be considered for HRG PEs/VPL ratio as per project proposal). Please check with respective SACS for modified ratio. | Staffing | 1 | There are total 18 PEs out of the sanctioned posts of 20 PEs. Each peer educator has a target of an average 44 HRGs.
6 | 50% of the PEs belong to the age group below 30 years or should match with the high /medium risk HRGs linelisted by the programme | Interact with all the peer educators for core TIs. The peer educators should be recruited at least 6 months and are trained by the project. | Staffing | 1 | Only two Peer educators are below the age of 30 years. The average age of the PE is 43.5 years. It was informed by the Project Manager that they have taken permission from the Chandigarh SACS regarding the over age of the PEs.
7 | For each set of 250 HRG there is an ORW has been appointed | Registration documents, MIS reprts, ORW records. (A 20% Variation may be considered for HRG PEs/VPL ratio as per project proposal). | Staffing | 1 | The average ratio of ORW:HRG is 1:162.
8 | Job description given to each project staff, atleast staffs are able to describe their job description and the same is reflected in their plans prepared for the programme during last 2 quarters | All project staff do have written job description or available at NGO level. If the programme manager and all ORWs are not able to describe their job responsibilities or the same is not reflected in their plans, the score should be '0' | Institutional Environment | 1 | Job description has been given to each staff member, attached in the respective personal files as well as displayed on the project's notice board.
9 | Attendance/leave register maintained for the project staff | Examine the attendance register is in use/leave register available | Administrative system | 1 | Attendance and leave register is mantained properly and duly verified by the Project Director.
10 | Does the NGO management takes into consideration the community needs/resources into consideration while planning/delivering services through arrangements like availability of programme management body represented by community/ community consultations. | Minutes of the community consultation/ programme management body represented by community members should reflect that such process is at least more than 6 months old, otherwise the score should be '0' | Institutional visioning / shared responsibility. | 1 | 6 meetings of Program Management Committee were held during the evaluation period.
11 | Induction training / orientation to PE and other staff has been completed by the TI project immedaitely after recruitment. | Training registers/ induction training report | Proper induction in place | 1 | 12 trainings (induction and in-house trainings) were conducted during the evaluation period (September, 2021 to October, 2022).
12 | The role of Governing Body members in addressing issues of crisis/stigma/discrimination faced by the community members by networking with stakeholders, by keeping well informed about the issues of HRGs | Meeting with at least 2/3 members of the GB and interview to focus on their role in the programme. Also meet at least the stake holders and assess the role played by the members. If oraganization not playe any role in addressing issues faced by HRGs, score should e '0'. | Understading of role of NGO in developing contusive environmrment. | 1 | 5 cases of crisis were identified during the evaluation period and the issues were resolved by the crisis management committee.
13 | The Project Director attended atleast 80% all the monthly meetings of the TI project duing the year. The PD has attended and initiated action against the areas of improvement based on the minutes. | Attendance of meeting registers and minutes of the meeting. Action taken report based on previous meeting. | Invovement of Project director in project activities. | 1 | 11 review meetings (monthly) were conducted during the evaluation period. All meetings were attended by the Project Director and the meeting minutes were duly verified by the Project Director.
14 | Assets purchased under project is codified/marked | Assets register and purchase voucher (All the assets purchased under the project) | Proper assest maintance system | 1 | Assets register is maintained properly, separately for OST center and TI project. All the project items are codified and verified.
Total Score |  |  |  | 14

## Finance
TI -Annual Evaluation Tool -2019-20 (FSW/MSM/IDU/TG)
Name of the NGO:SOSVA |  |  | District:Chandigarh |  | State:
Finance
Sl.No. | Indicators | Key Questions | Methodology to be adopted | Score |  | Score Resulted "0" for No "1" for Yes | Explanation for score | Remarks
|  |  |  | 1 | 0
1 | Budget Utilization | What is the percentage of budget utilized against the release of fund on the proposed activities | Verification of vouchers, SOE, Bank book etc.. | Utilization should be of or above 60% against the release of fund from SACS | Less than 60% of the released fund | 1 | Budget Utilised in 2021-22 is more than 60% . TI account - 95% OST- 56 - 90% OST 38-77% But it is less than 60% in 2022-23. | Fund utilisation of year 2022-23 is less than 60% and advised to use the funds till March 2023.
2 | Pattern of expenditure | Whether the expenditure is as per approved budget in each head | Verification of vouchers, approved budget, SOE, Bank book etc.. | As per the approved budget or No but as per the approval from SACS. | No as per the approval. | 1 | All the expenditure done as per approved budget.
3 | Bank Account | Whether a separate bank account maintained for the TI Project at the local bank | Verification of bank book and other related documents | Separate bank account in place for TI project in the project area | No separate account | 1 | Separate account in State Bank of India Sector- 17 but it is joint account for T I, OST-56 and OST-38.
4 | Systems of Payment-Verification of Bills and Vouchers ( in case of book keeping is done by software, day wise prints of vouchers and ledgers should be available) | All payments made with proper bills and vouchers and are in place with proper approval along with the PFMS advice. | Verification of vouchers and bills | Vouchers and bills are propoerly maintained and are all with approval. | Inadeqaute and no approval from PD of the TI. | 1 | All vouchers / bills are in serial order and proper maintained with approval. | It is advised to mention proper head on voucher and book the expenditure in proper head. ( Refer Voucher no. 1737)
5 | The PFMS portal is active | All the payments to the staff and vendors are done through the PFMS portal and advice is kept. | Verification of vouchers and bills | PFMS portal is used for all transactions | PFMS portal is not used for of transactions | 1 | No Cash transaction done above Rs. 5000/-
6 | Systems of Payment/Mode of payments | All payment is through cheque/PFMS is Rs.5000/- as per revised direction from NACO. | Verification of bank account and vouchers | No cash transaction above Rs.5000/- | Cash transaction for the amount more than Rs.5000/- | 1 | Vouchers are printed and in serial order and Ledger is maintained properly. | It is advisable to mention the balance in ledger and it should be signed and stamped by Accountant and Project Manager.
7 | Systems of Payment-Record keeping | All vouchers are printed and machine numbered. Whether the ledger is maintained accordingly for vouchers | Verification of vouchers Verification of ledger | Vouchers are printed and machine numbered. Ledgers are maintained properly. | Not in place. | 1 | Cash book is updated and signed and stamped by Project Manager & Project Director at the end of every month. | It is advisable to mention the Voucher no. in Cash book and book the expenditure in proper head. ( Refer Page no. 20 of cash book. Needles / Syringes booked under head of Office expenses of Rs. 3968)
8 | Systems of booking keeping maintenance | Whether cash book maintained/entry made on daily basis | Verification of cash book and interview of accountant | Cash book is updated | Not updated | 1 | SOEs are submitted on time to SACS and maintained in proper manner.
9 | Financial reporting-SOEs submitted as per operational guideline | Whether SOEs are submitted to SACS on time in the prescribed format. | Verification of SOEs and interview of SACS official | SOEs are submitted on time and records for the same is avaialbe. | Irregualr in submission of SOEs. | 1 | Nil and Negligible mismatch found.
10 | Financial reporting-Mismatch between physical & financial reporting | Whether any mismatch between financial and physical progress reports | Verification of MIS reports and audit reports | Nil or Negligible mismatch | Huge level of mismatch observed and not justifiable | 1 | Action taken report on audit recommendations is submitted on time and a separate file is maintained for it
11 | Compliance to SACS directions | Whether NGO has complied to the audit observations | Verify audit recommendation and action taken bassed on the report | NGO has given adeqaute attention to audit recommendations and actions were taken | No action from NGO side | 1 | All payments / Transactions done through PFMS. | File of PFMS advices shuold be place at TI office.
12 | Procurement system in place | What is the procurement system for purchase of drugs/needles and syringes/fixed assets/ etc | Three quotations to be collected ( Not needed where the supply is from governemt machanism) | Quotations are in place from three different parties and assessed. | No system in place, either by the NGO or Government system is in place | 1 | Quotation file present in TI Office and comparative statement is in place to purchanse any medicine / fixed asset etc.
Total Score | [5 empty] | 12

## Scoring sheet FSW-MSM-TG
Scoring Sheet for FSW/MSM -2019
Name of the NGO: |  |  | District: |  | State:
Calculation of score for stage 1
S. No. | Particulars | Maximum no. of indicators | Max. Score | Minimum Qualifying Marks | Minimum Qualifying Percentage
Stage1
1 | Organisational Capacity | 14 | 14 | 11 | 78.5714
2 | Finance | 12 | 12 | 8 | 66.6667
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Status-Qualified/ not Qualified | Remarks
1 | Organisational Capacity | 14 | 14 | 100 | Qualified
2 | Finance | 12 | 12 | 100 | Qualified
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S. No. | Particulars | No. of indicators | Max. Score | Maximum weighted Score | Actual Score Obtained | Actual Weighted Score obtained | Percent score obtained
1 | BASIC SERVICES | 17 | 51 | 40.8 | 56 | 44.8 | 109.8039
2 | SUPPORT SERVICES | 10 | 30 | 15 | 27 | 13.5 | 90
Total |  | 27 | 81 | 55.8 | 83 | 58.3 | 104.4803
Name of the Evaluators

## Scoring sheet-IDU
Scoringn sheet for IDU-2019
Name of the NGO: |  |  | District: |  | State:
Calculation of score for stage 1
S. No. | Particulars | Maximum no. of indicators | Max. Score | Minimum Qualifying Marks | Minimum Qualifying Percentage
Stage1
1 | Organisational Capacity | 14 | 14 | 11 | 78.5714
2 | Finance | 12 | 12 | 9 | 75
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Status-Qualified/ not Qualified | Remarks
1 | Organisational Capacity | 14 | 14 | 100 | Qualified
2 | Finance | 12 | 12 | 100 | Qualified
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S. No. | Particulars | No. of indicators | Max. Score | Maximum weighted Score | Actual Score Obtained | Actual Weighted Score obtained | Percent score obtained
1 | BASIC SERVICES | 23 | 69 | 55.2 | 56 | 44.8 | 81.1594
2 | SUPPORT SERVICES | 10 | 30 | 15 | 27 | 13.5 | 90
Total |  | 33 | 99 | 70.2 | 83 | 58.3 | 83.0484
Name of the Evaluators: Dr Sukhbir Singh, Dr Nidhi Jaswal and Ms. Bhawna Saini

## Scoring sheet-CC
Scoringn sheet for Core-composite TI-2019
Name of the NGO: |  |  | District: |  | State:
Calculation of score for stage 1
S. No. | Particulars | Maximum no. of indicators | Max. Score | Minimum Qualifying Marks | Minimum Qualifying Percentage
Stage1
1 | Organisational Capacity | 14 | 12 | 8 | 66.6667
2 | Finance | 12 | 12 | 8 | 66.6667
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Status-Qualified/ not Qualified | Remarks
1 | Organisational Capacity | 14 | 14 | 100 | Qualified
2 | Finance | 12 | 12 | 100 | Qualified
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S. No. | Particulars | No. of indicators | Max. Score | Maximum weighted Score | Actual Score Obtained | Actual Weighted Score obtained | Percent score obtained
1 | BASIC SERVICES | 17 | 51 | 40.8 | 56 | 44.8 | 109.8039
2 | SUPPORT SERVICES | 10 | 30 | 15 | 27 | 13.5 | 90
Total |  | 27 | 81 | 55.8 | 83 | 58.3 | 104.4803
Name of the Evaluators
9

## Scoring sheet-CC With IDU
Scoringn sheet for Core-composite TI-2019
Name of the NGO: |  |  | District: |  | State:
Calculation of score for stage 1
S. No. | Particulars | Maximum no. of indicators | Max. Score | Minimum Qualifying Marks | Minimum Qualifying Percentage
Stage1
1 | Organisational Capacity | 14 | 12 | 8 | 66.6667
2 | Finance | 12 | 12 | 8 | 66.6667
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Status-Qualified/ not Qualified | Remarks
1 | Organisational Capacity | 14 | 14 | 100 | Qualified
2 | Finance | 12 | 12 | 100 | Qualified
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S. No. | Particulars | No. of indicators | Max. Score | Maximum weighted Score | Actual Score Obtained | Actual Weighted Score obtained | Percent score obtained
1 | BASIC SERVICES | 24 | 72 | 57.6 | 56 | 44.8 | 77.7778
2 | SUPPORT SERVICES | 10 | 30 | 15 | 27 | 13.5 | 90
Total |  | 34 | 102 | 72.6 | 83 | 58.3 | 80.303
Name of the Evaluators
9