## Organisational Capacity
TI-Evaluation Tool Truckers
Organisational Capacity
Name of the TI NGO: |  |  | Intervention Category: A/B/C (please circle the required one) | State: District:
Sl.No. | Indicators | Score Resulted "0" for No "1" for Yes | Mean of verification/observations | Remarks
1 | All project staff and 70%PE positions have been filled as per project proposal | 1 | All NGOs contracted has to appoint the staff within three months from signing of contract. Project proposal, staff attendance sheet during the last year (If a position has been vacated and not filled in within 2 months, give "0" mark for this indicator.) | All Project staff including Project Manager, Counselor, M&E officer, 4 ORWs are in position. The staff retention during the evaluation period is more than 85%.
2 | Staff turnover witnessed in the project during the contract period. | 1 | Attendance sheets /appointment letters. ( If there is more than 50% of project staff(except PEs) have resigned during the year then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | Only one ORW has resigned during the evaluation period. The new ORW joined within one month of resignation.
3 | Peer Educator turnover witnessed in the project during the contract period | 1 | Attendance sheets /appointment letters. ( If there is more than 20% PEs during the contract period then this indicator will be awarded '0'). If the replacement for a position is not done within two months should also be awarded "0". | There are 10 Peer educators in the project. Two Peer educators resigned during the evaluation period but were replaced within one months time.
4 | Job description given to each project staff | 1 | All project staff do have written job description or available at NGO level | Job description is given to all the project staff members. But are not displayed in the office premises.
5 | Peer Profile | 1 | More than 20% of all the Pes are truckers /ex truckers, helpers /ex helpers | Around 50% of the Peer educators are helpers, auto mechanic, and ex-truckers.
6 | Attendance/leave register maintained for the project staff | 1 | Examine the attendance register is in use /leave register available | Attendance and leave register are maintained by the proejct staff. 12 keaves are sanctioned for one year (April to March)
7 | Orientation to PE and other staff has been completed | 1 | Training registers/ orientation training/PO visit report completed within 3 months of joining | All staff members including newly recruited ORW and peers have received the
8 | The project Director attended atleast 60% all the monthly meetings of the TI project duing the year. | 1 | Attendance of meeting registers and minutes of the meeting | 1 review meeting is held every month and is attended by the Project Coordinator and once in every quarter is attended by the Project Director. The meeting minutes are maintained but without action taken report.
9 | Assets purchased under project is codified/marked | 1 | Assets register and purchase voucher (All the assets purchased under the project) | All assets purchased under the project are codified. Assets register is maintained properly and is up to date.
Total Score |  | 8
Name of the Evaluator

## Finance
TI - ANNUAL EVALUATION
Evaluation Tool for Finance
Name of the TI NGO:TCI Truckers |  |  | Intervention Category: B(please circle the required one) |  | State: Chandigarh District: Chandigarh
Sl.No. | Indicators | Key Questions* | Methodology to be adopted | Score |  | Score Resulted "0" for No "1" for Yes | Explanation for score | Remarks
|  |  |  | 1 | 0
1 | Budget Utilization | What is the percentage of budget utilized against the release of fund on the proposed activities | Verification of vouchers, SOE, Bank book etc.. | Utilization should be of or above 60% against the release of fund from SACS | Less than 60% of the released fund | 1 | Budget Utilised in 2021-22 is 95% and In 2022-23 is 98%.
2 | Pattern of expenditure | Whether the expenditure is as per approved budget in each head | Verification of vouchers, approved budget, SOE, Bank book etc.. | As per the approved budget or No but as per the approval from SACS. | No as per the approval. | 1 | All the expenditure done as per approved budget.
3 | Bank Account | Whether a separate bank account maintained for the TI Project at the local bank | Verification of bank book and other related documents | Separate bank account in place for TI project in the project area | No separate account | 1 | There was a separate account of TI in Kotak Mahindra bank but it is closed now. and CNA account opening is in process.
4 | Systems of Payment-Verification of Bills and Vouchers ( in case of book keeping is done by software, day wise prints of vouchers and ledgers should be available) | All payments made with proper bills and vouchers and are in place with proper approval. | Verification of vouchers and bills | Vouchers and bills are propoerly maintained and are all with approval. | Inadeqaute and no approval from PD of the TI. | 1 | All Vouchers and bills are properly maintained and with approval.
5 | Systems of Payment-Mode of payments | Mode of payment- cash payment is Rs.5000/- as per revised direction from NACO. | Verification of bank account and vouchers | No cash transaction above Rs.5000/- | Cash transaction for the amount more than Rs.5000/- | 1 | No Cash transaction done above Rs. 5000/-
6 | Systems of Payment-Record keeping | All vouchers are printed and machine numbered Whether the ledger is maintained for vouchers | Verification of vouchers Verification of ledger | Vouchers are printed and machine numbered. Ledgers are maintained properly. | Not in place. | 1 | Vouches are Printed and Machine numbered and Ledger book is properly maintained by Accountant. Cash book Folio number is properly mentioned in ledger book.
7 | Systems of booking keeping maintenance | Whether cash book maintained/entry made on daily basis | Verification of cash book and interview of accountant | Cash book is updated | Not updated | 1 | All the expenditure booked in cash book in proper manner and voucher no. and Ledger folio no. is properly mentioned.
8 | Financial reporting-SOEs submitted as per operational guideline | Whether SOEs are submitted to SACS on time in the prescribed format. (refer Operational Guidelines for NGO/CBO PART-II-Annexure 'A' and 'B' | Verification of SOEs and interview of SACS official | SOEs are submitted on time and records for the same is avaialbe. | Irregualr in submission of SOEs. | 1 | SOEs are submitted on time to SACS and maintained in proper manner.
9 | Financial reporting-Mismatch between physical & financial reporting | Whether any mismatch between financial and physical progress reports | Verification of MIS reports and audit reports | Nil or Negligible mismatch | Huge level of mismatch observed and not justifiable | 1 | Nil and Negligible mismatch found.
10 | Purchase of drugs for STD treatment (only in cases where the purchase has been approved by SACS) | Whether the guidelines on GMP followed? | Verify the drugs and guidelines for GMP/ purchased under Jan Ausadhi Yojana | As per GMP | Not followed and no genuine explanation for the relapse | 1 | Action taken report on audit recommendations is submitted on time.
11 | Compliance to SACS directions | Whether NGO has complied to the audit observations | Verify audit recommendation and action taken bassed on the report | NGO has given adeqaute attention to audit recommendations and actions were taken | No action from NGO side | 1 | All payements / Transactions done through PFMS and printed advices were enclosed with vouchers and bills.
12 | The PFMS portal is active | All the payments to the staff and vendors are done through the PFMS portal and advice is keept. | Verification of vouchers and bills | PFMS portal is used for all transactions | PFMS portal is not used for of transactions | 1 | Quotation file present in TI Office and comparative statement is in place to purchanse any medicine / fixed asset etc.
13 | Procurement system in place | What is the procurement system for purchase of drugs/needles and syringes/fixed assets | Three quotations to be collected | Quotations are in place from three different parties and assessed. | No system in place. | 1
Total Score | [5 empty] | 13
Name of the Evaluator

## Program Delivery
TI Evaluation Tool for Truckers 2019-20
Programme Delivery
Name of the TI NGO:TCI Truckers |  |  |  |  | Intervention Category: B |  | State: Chandgarh District:Chandigarh
Sl No | Indicators | Target | Achievement | Key Questions | Methodology to be adopted | Assessment Scores |  |  | Scores Resulted | Remarks
[6 empty] | 1 (Poor) | 2 (Average) | 3 (Good)
Outreach
1 | Monthly outreach plan in place at project level available for each truckers halting point within the project area. i.e. one project area may have separate truck halting points and each require separate plan. |  |  | Verification of outreach plan | Interview with ORWs and Pes whether they are able to explain the plan and its use.Mark 0 if outreach plan is not there for past 3 months | Outreach plan in place but ORW not able to explain | Outreach plan in place able to explain but not fully used by Team. | Outreach plan in place and the same is used by ORW, and PE. | 2 | outreach plan is in place but able to explan
2 | Percent of target truckers contacted by the project through IPC sessions (as per intervention wise contract per year) | 1,20,000 for A category, 40,000 for B category, 20,000 for C category. | 10000/ | Number of estimated truckers contacted through IPC sessions conducted by Pes and ORWs at least once in a quarter during contract year as per contract agreement.1,20,000 for A category,40,000 for B category,20,000 for C category. | [5/ | At least 40% of target truckers contacted through IPC sessions in a quarter during the contract period | 41-59% of target truckers contacted through IPC sessions in a quarter during the contract period. | More than 60% of target truckers contacted through IPC sessions in a quarter during the contract period. | 3 | In a quarter, IPC sessions were conducted more than 80% of the target.
3 | Field Visit by ORWs | 5 days a week and 2 days for supervision for each ORW |  | ORW visiting the field minimum 5 days in a week and providing 2 day supportive supervision to all the PEs of his/her areas for effective delivery of project services by PEs to truckers . 60% ORWs are able to demonstrate IPC sessions/Health games. | ORW diaries, weekly staff meeting minutes, ORW movement plan/register,observations on field recorded in the diaries. If no field visit, score is '0' | Atleast 40% among the ORWs are able to demonstrate IPC sessions/Health games | Atleast 50% among the ORWs are able to demonstrate IPC sessions/Health game | All ORWs are able to demonstrate IPC sessions/Health game | 3 | ORWs are aware of IPC and are demonstrating IPC sessions in the field. ORW are visiting the field to supervise the peer educator sessions.
4 | Theme based street plays | 30/permonth for A category,10/monthfor B category,5/month for C category | 26 | Number of street plays organised against plan during last three months.30/permonth for A category,10/monthfor B category,5/month for C category | Review of Daily report (ORW), Mid-media /IPC report, BCC material distribution register, Monthly report (Quantitative and Qualitative), Review of scipt, Personal observation and interactions | At least 50% street play organised against planned | At least 51-80% street play organised against planned | 80% and above street play organised against planned | 3 | 29 Street Paly has been planned, and 29 are being organised.
5 | Quality of peer education by the Peers |  |  | Observation of atleast 2 IPC sessions and interaction with the peers | Review of IPC Charts.Personal observations and interactions with Peers | Less than 40% PEs interacted are able to demonstrate right way of conducting IPC sessions and condom demonstration | 41-59% PEs interacted are able to demonstrate right way of conducting IPC sessions and condom demonstration | 60% and above Pes interacted are able to demonstrate right way of conducting IPC sessions and condom demonstration. | 3 | Peer educators can easily demonstrate the IPC session in their native language and are confident in running the sessions.
Clinic and other Services
6 | Established static clinic and operates at flexible timings with required manpower, infrastructure and equipment/instruments |  |  | Set up of a static clinic (may also be of flexible timings) as per NACO guidelines (Doctor,Counselor/staff nurse),timings of atleast 3 hours a day, space for examination available, STI drugs availabilty. | Clinic observations based on NACO guidelines/ checklist.Observation and interaction with Doctor,counselor//Staff nurse. | Static clinic set up without proper clinical equipment, non availabilty of STI drugs. | Static clinic set up with proper clinical equipment but non availabilty of STI drugs as per guidelines. | Static clinic set up with proper clinical equipment, Availabilty of STI drugs with proper stock keeping | 3 | One static clinic has been set up with the necessary clinical equipment. In the office, STI drugs are available.
7 | Quality of clinical services provided by the static/satelite clinics |  |  | Clinical services provided with confidentiality, patients are counseled on condom use, follow up plan is discussed. | Observations of the services, feedback from the truckers and stakeholders. | Confidentiality is not maintained, follow up plan is not discussed | Confidentiality is maintained, other factors are compromised. | All basic requirements are met. | 3 | During interactions with the community, it was discovered that they are satisfied with the services. Counselling is provided to all the patients.
8 | Operates satelite clinics, as extension of static clinics around neighbouring establishments accessible by truckers |  |  | Operates satellite clinic (as per NACO guidelines) around neighbouring establishments .3-6 satellite locations in A category site,3 atellite locations in B category, Not applicable in C category site. | Clinic observations based on NACO guidelines/ checklist. Clinic schedules prominently displayed at transporters/brokers premises. | Satellite clinic non operational | Satellite Clinic operational but less than 3 locations | Satellite clinic operational and in 3-6 locations . | 3 | Satellite clinic operational and in 3 locations
9 | Truckers screened/tested for HIV through CBS/ICTC | 100% of STI cases need to tested for HIV | CBS=1212 ICTC=3473 Total=4685 | Percent of truckers registered for STI treatment were tested for HIV testing | Couseling and referal registered/CMIS, verification of referral slips signed by ICTC counselor | Below 30% of referred to ICTC have actually tested in ICTC | 31-39% of referred to ICTC have actually tested in ICTC | Above 40% of referred to ICTC have actually tested in ICTC | 1 | 23.2 referred to ICTC have actually tested in ICTC
10 | STI counseling sessions | 100% of STI cases need to be counseled | 56 | Project Counselor is adequately trained and performs STI counseling | Counseling Register, Personal interaction and observations during the counseling session | Below 50% of the STI clients are exposed to STI counseling | 50-80% STI clients in the clinic are exposed to STI counseling | 80% and above STI clients are exposed to STI counseling. Counselor adheres to all steps | 3 | All the STI cases hase been counselled by the counsellor.
11 | Co-Branding of Suraksha clinics and IEC/BCC materials |  |  | Clinic walls have colour combination of Yellow and Blue. IEC/BCC materials are displayed with logos of Suraksha clinic | Personal observations | Clinic not functional | Clinic functional without Khushi/Suraksha Branding (Wall colours and logos) | Clinic functional with Khushi/Suraksha branding (wall colours and logos) | 3 | Clinic walls have colour combination of Yellow and Blue. IEC/BCC materials are displayed with logos of Suraksha clinic
12 | Clinic footfalls in the clinics (15% of coverage for A category and 25% of coverage for B&C category of the outreach coverage - indicator no.2) | 15% of coverage for A category and 25% of coverage for B&C category of the outreach coverage - indicator no.2) | 10767 | The clinic footfalls observed during last 3 months ( average of 3 months) to be taken | Verification of clinic cards, patient register, medicine dispensing register, cash book | Less than 15% in A, 25% in B &C | 15% in A, 25% in B&C | More than the benchmark | 3 | In the last three months, the TI clinic has seen 2548 clinic footfall.
13 | STI footfalls among the clinic footfalls (10% of the foot falls - indicator 12) | 10% of the foot falls - indicator 12 | 14 | The STI footfalls observed during last 3 months ( average of 3 months) to be taken | Verification of clinic cards, patient register, medicine dispensing register, cash book | Less than 10% of the above indicator | 10% of the above indicator | More than 10% of the above indicator | 1 | Only 14 STI footfalls have been observed in the clinic over the last three months.
Condom Management
14 | Coordination with the SMO to provide information on condom availablity, demand, avaiability and display of IEC on condoms. In case of non-SMO districts the NGOs are expected to manage social marketing |  |  | Joint planning, field visits and reviews held with SMO | Meeting minutes and Joint visit reports with SMO. Feedback from the out let holders, SMO supervisors of the area. | Joint reviews, planning and field visits with SMO/ TSG POs done for less than 6 months | For 6-10 months, Joint reviews, planning and field visits with SMO/ TSG POs | Joint reviews, planning and field visits with SMO/TSG POs done for more than 10 months | 3 | Joint reviews, planning and field visits with SMO done for more than 10 months as per the records
15 | Traditional and non-traditional outlets for condom social marketing | At least 80% of the out lets should be non-traditional | 50 | Percent of traditional and non-traditional outlets for condom social marketing in the operational area | Daily dairies , Weekly and monthly reports, SM Condom register | Below 50% of the functional TO and NTO available as per the target | Between 50-80% functional TO and NTO available as per the target | 80% and above functional TO and NTO available as per the target | 3 | All the condom outlets are non traditional.
16 | Condoms sales through the TO and NTO | At least 80% of the condom sales through outlets | 45195 | Percent of condoms sold through the TO and NTO in the oprational area | Daily dairies, , Weekly and monthly reports, SM Condom register | Below 50% condom sale recorded as per the target | Between 50-80% condom sale recorded as per the target | 80% and above condom sale recorded as per the target | 3 | Condom Demnad=97500 Condom Distribution= 99690
17 | STI Drugs -commodity-drug management, availability, stock out. |  |  | Whether NGO purchases drugs using 3 competitive quotations, medicines dispensed to the truckers at no-profit basis, receipts are maintained. | Medicine stock register, Cash Book, bills, receipts. In case of stock outs and no procument score is '0' | Medicines procured with out quotations/ no receipts maintained for dispensing | Medicines procured with proper quotations but no receipts maintained for dispensing | Medicines procured with proper quotations and receipts maintained for dispensing | 3 | Medicines procured with proper quotations and receipts maintained for dispensing
SECTION 2: SUPPORT SERVICES
Enabling Environment
18 | Involvement of different stakeholders in the project activities through constitution of Local Advisory Committee ( A committee comprised of members from brokers, associations, owners, other stakeholders of the project area) |  |  | ` | Verification of the LAC Register and interaction with LAC members(Byelaw if available) .LAC not constituted, then score is '0'. | LAC constituted but meetings not held in last 6 months. | LAC constituted meetings are held but members are not aware of their role. | LAC constituted and members updated on the project activities in the meetings in last 3 months | 3 | LAC constituted and members updated on the project activities. In last 3 months 12 meetings has been attended.
Community response to the Program Services
19 | Project is adhereing to confidentiality norms |  |  | Confidentiality is maintained for the counseling sessions | FGD with the 10-15 truckers (suggested to conduct at the field). | Participants are not sure of confidentiality norms being adhered at the project level | Atleast 50% of the participants are satsfied with privacy and confidentiality at the project level. | More than 50% of the particiaptns are satsfied with privacy and confidentiality at the project level. | 3 | There is an independent counselling room. Respondents are satisfied with the counselling services.
20 | Community perception on project services |  |  | Are the truckers satisfied with the available services and services meet their 3demands. | FGD with 5-10% brokers/transporters/truckers (suggested to conduct at the filed level). | Atleast 40% of the truckers are convinced with the project services | 41%- 60% truckers are satisfied with the project services. | More than 60% or of the truckers are satisfied with the project services. | 3 | During the focus group with truckers and transporters, it was revealed that they are extremely satisfied with the services.
21 | Adequate supply of commodities (condoms) |  |  | Condoms through Social Marketing provided by the Project | FGD with 10-15 community members (Suggested to conduct at the filed) | at least 50 % respondents reported that they are getting the condoms as and when they demand. | 51-75% respondents reported that they are getting the condoms as and when they demand. | More than 80% or of the respondents reported that they are gettingthe condoms as and when they demand. | 3 | During interactions with community members, it was discovered that they are receiving condoms on demand.
22 | Involvement of key stakeholders in program monitoring |  |  | Ability of the project to involve key stakeholders in addressing the issues relating to project activities and providing support to the project team | One to one interaction with atleast 3 stakeholders of the project. (suggested to conduct at the filed). | At least 1 stake holders participated and provided support in project activities | At leat 2stake holders participated and provided support in project activities | More than 2 stake holders participated and provided support in project activities | 3 | The TI evaluation team met with four stakeholders on the ground, including the president of the Chandigarh Transport Association. All stakeholders are actively involved in the planning and execution of TI activities.
23 | Involvement of Counselor |  |  | The counsellor should be sensitive while addressing issues relating to truckers. | FGD with the 10-15 community members (suggested to conduct at the field level). | Atleast 50% respondents reported that they are satisfied with the counselor/ANM | 51 to 75% respondents reported that they are satisfied with the counselor/ANM | More than 75% or of the respondents reported that they are satisfied with the counselor/ANM | 3 | Two focus groups were held with community members, and it was discovered that the trucekrs and cleaners were very satisfied with the counselling services provided by the counsellors.
SECTION 1: BASIC SERVICES | [5 empty] | SECTION 1: TOTAL MARKS OBTAINED |  |  | 46
SECTION 2: SUPPORT SERVICES | [5 empty] | SECTION 2: TOTAL MARKS OBTAINED |  |  | 18
TOTAL SCORE | [8 empty] | 64
Name of the Evaluator

## Score sheet
Scoring Sheet Truckers
Name of the TI NGO: |  |  | State: |  | District:
Calculation of score for stage 1
| Particulars | Maximum no. of indicators | Max. Score | Qualifying Marks | Qualifying Percentage
Stage1
1 | Organisational Capacity | 9 | 9 | 7 | 80
2 | Finance | 13 | 13 | 9 | 70
Actual Marks ( calculated automatically from the evaluation sheet)
| Particulars | Max. Score | Actual Marks Obtained | Percent of Marks | Qualified/Not Qualified |  | Remarks
1 | Organisational Capacity | 9 | 9 | 100
2 | Finance | 13 | 13 | 100
Calculation of score for stage 2
Weightage Score from Program Delivery (calculated automatically from the evaluation sheet)
S NO | Particulars | No. of indicators Applicable for this TI | Maximum Score | Maximum weighted Score | Score obtained | Weighted score obtained | Percent of Score derived
1 | Basic services | 17 | 51 | 40.8 | 46 | 36.8 | 90.1961
2 | Support services | 6 | 18 | 9 | 18 | 9 | 100
Total Marks |  | 23 | 69 | 49.8 | 64 | 45.8 | 91.9679
Name of the Evaluator : Dr Sukhbir Singh, Dr Nidhi Jaswal and Ms. Bhawna Saini